## Failure Categories
KITE issue | Test Env issue | ICB issue (Once) | ICB issue (Always) | TS issue | Human error | SRL/CR changes
CAN Signal Issue | Automation Setup Malfunction | Once Seen | Valid Issue |  |  | SRL Change
Image Comparision | External Hardware Setup Malfunction | GAS Implementation | Timing Issue |  |  | Timing Issue
Audio Comparision | External Application Issue | Timing Issue
Video Comparision | Network Issue
Robot Touch Operation
Device Mapping Issue
KITE Application Issue

## Format
Label | Jira ID | Test Script ID | Bench Number | Test Pack Name | Date | Result | Failure Category | Failure Sub Category | Root Cause Details | Fixation Performed | Issue fixed ? | Additional Information | Transition
| DRT-4028 | KPIT_TC_DRT_AVG_223 | Bench09_TYAW_DEV | B09_14_TYAW_Q_KA_AVG | 21st May 2025 | Fail | Test Env issue | Automation setup malfunction | Amplifier power cable disconnected. | Resolved by hardware engineer
1407 REL 22/05/2025 |  | KPIT_TC_DRT_USB_140 |  |  | 22/05/2025 | Fail | Test_Env_Issue | Automation Set up malfunction | USB Disconnected.
1407 REL 22/05/2025 |  | KPIT_TC_DRT_AVC_091 |  |  | 22/05/2025 | Fail | KITE_Issue | Image Comparison | Image comparison failed with 83% | Tested Manually: Pass
1407 REL 22/05/2025 |  | KPIT_TC_DRT_IDS_014 |  |  | 22/05/2025 | Fail | Test_Env_Issue | Automation Set up malfunction | CAN Signal not reflecting on ICB
POSTCS4 22/05/2025 |  | KPIT_TC_DRT_LWC_002 |  |  | 22/05/2025 | Fail | ICB Issue | Valid Issue | Camera" settings option is not displayed on "General Settings" screen(PJ04DEF00-3360)
POSTCS4 22/05/2025 |  | KPIT_TC_DRT_LWC_001 |  |  | 22/05/2025 | Fail | ICB Issue | Valid Issue | Camera" settings option is not displayed on "General Settings" screen(PJ04DEF00-3360)
POSTCS4 22/05/2025 |  | KPIT_TC_DRT_IVI_037 |  |  | 22/05/2025 | Fail | ICB Issue | Valid Issue | Camera" settings option is not displayed on "General Settings" screen(PJ04DEF00-3360)
POSTCS4 22/05/2025 |  | KPIT_TC_DRT_INL_008 |  |  | 22/05/2025 | Fail | ICB Issue | Valid Issue | "Start Diag" and "Exit Diag" options are not enabled on Inline Diagnosis screen(PJ04DEF00-3362)
POSTCS4 22/05/2025 |  | KPIT_TC_DRT_IVI_044 |  |  | 22/05/2025 | Fail | ICB Issue | Valid Issue | Camera" settings option is not displayed on "General Settings" screen(PJ04DEF00-3360)
POSTCS4 22/05/2025 |  | KPIT_TC_DRT_LWC_004 |  |  | 22/05/2025 | Fail | ICB Issue | Valid Issue | Camera" settings option is not displayed on "General Settings" screen(PJ04DEF00-3360)
POSTCS4 22/05/2025 |  | KPIT_TC_DRT_IVI_046 |  |  | 22/05/2025 | Fail | ICB Issue | Valid Issue | Camera" settings option is not displayed on "General Settings" screen(PJ04DEF00-3360)
POSTCS4 22/05/2025 |  | KPIT_TC_DRT_LWC_003 |  |  | 22/05/2025 | Fail | ICB Issue | Valid Issue | Camera" settings option is not displayed on "General Settings" screen(PJ04DEF00-3360)
POSTCS4 22/05/2025 |  | KPIT_TC_DRT_PKS_011 |  |  | 22/05/2025 | Fail | ICB Issue | Valid Issue | Camera" settings option is not displayed on "General Settings" screen(PJ04DEF00-3360)
POSTCS4 22/05/2025 |  | KPIT_TC_DRT_INL_024 |  |  | 22/05/2025 | Fail | ICB Issue | Valid Issue | "Start Diag" and "Exit Diag" options are not enabled on Inline Diagnosis screen(PJ04DEF00-3362)
POSTCS4 22/05/2025 |  | KPIT_TC_DRT_INL_010 |  |  | 22/05/2025 | Fail | ICB Issue | Valid Issue | "Start Diag" and "Exit Diag" options are not enabled on Inline Diagnosis screen(PJ04DEF00-3362)
POSTCS4 22/05/2025 |  | KPIT_TC_DRT_IDS_014 |  |  | 22/05/2025 | Fail | Test_Env_Issue | External Hardware Setup Malfunction | CAN Signals not reflected
REL 27/05/2025 |  | KPIT_TC_FNC_FM_0638_0001 |  |  | 27/05/2025 | Fail | KITE_Issue | Image Comparison | Image Comparison failed with 79% | Tested Manually: Pass
REL 27/05/2025 |  | KPIT_TC_DRT_AVC_091 |  |  | 27/05/2025 | Fail | KITE_Issue | Image Comparison | Image Comparison failed with 84% | Tested Manually: Pass
REL 27/05/2025 |  | KPIT_TC_DRT_IDS_014 |  |  | 27/05/2025 | Fail | Test_Env_Issue | External Hardware Setup Malfunction | CAN Signals not reflected | Tested Manually: Pass
REL 29/05/2025 |  | KPIT_TC_FNC_BZA_0026_0001 |  |  | 29/05/2025 | Fail | Test_Env_Issue | External Hardware Setup Malfunction | USB Disconnected for a moment | Tested Manually: Pass
REL 29/05/2025 |  | KPIT_TC_DRT_SPCCP_037 |  |  | 29/05/2025 | Fail | Test_Env_Issue | External Hardware Setup Malfunction | Carplay not connected | Tested Manually: Pass
REL 29/05/2025 |  | KPIT_TC_DRT_SPCCP_103 |  |  | 29/05/2025 | Fail | Test_Env_Issue | External Hardware Setup Malfunction | Carplay not connected | Tested Manually: Pass
REL 29/05/2025 |  | KPIT_TC_DRT_SPCCP_097 |  |  | 29/05/2025 | Fail | Test_Env_Issue | External Hardware Setup Malfunction | Carplay not connected | Tested Manually: Pass
REL 29/05/2025 |  | KPIT_TC_DRT_SPCCP_096 |  |  | 29/05/2025 | Fail | Test_Env_Issue | External Hardware Setup Malfunction | Carplay not connected | Tested Manually: Pass
REL 29/05/2025 |  | KPIT_TC_DRT_AVC_091 |  |  | 29/05/2025 | Fail | Test_Env_Issue | External Hardware Setup Malfunction | Wired AA not connected | Tested Manually: Pass
REL 29/05/2025 |  | KPIT_TC_DRT_IDS_014 |  |  | 29/05/2025 | Fail | Test_Env_Issue | External Hardware Setup Malfunction | CAN Signals not reflected | Tested Manually: Pass
DEV 03/06/2025 |  | KPIT_TC_DRT_AVC_091 |  |  | 2025-03-06 | Fail | Test_Env_Issue | Automation Set up malfunction | Basler camera brightness issue; image comparison failed by 84%
DEV 03/06/2025 |  | KPIT_TC_DRT_IDS_014 |  |  | 2025-03-06 | Fail | Test_Env_Issue | External Hardware Setup Malfunction | CAN Signals not reflected
1409DEV 04/06/2025 |  | KPIT_TC_DRT_AVC_091 |  |  | 2025-04-06 | Fail | Test_Env_Issue | Automation Set up malfunction | Basler camera brightness issue; image comparison failed by 84% | Daytime manually exe cuted 2 iteration Pass
1409DEV 04/06/2025 |  | KPIT_TC_DRT_IDS_014 |  |  | 2025-04-06 | Fail | Test_Env_Issue | External Hardware Setup Malfunction | CAN Signals not reflected | Daytime manually exe cuted 2 iteration Pass
1407 DEV 05/06/2025 |  | KPIT_TC_DRT_CLK_007 |  |  | 2025-05-06 | Fail | Test_Env_Issue | Automation Set up malfunction
1407 DEV 05/06/2025 |  | KPIT_TC_DRT_AMFM_196 |  |  | 2025-05-06 | Fail | Test_Env_Issue | Automation Set up malfunction | "IS_SECTION_PRESENT" command Fail, Section present on screen ROI 80% comapred
1407 DEV 05/06/2025 |  | KPIT_TC_DRT_IDS_014 |  |  | 2025-05-06 | Fail | Test_Env_Issue | External Hardware Setup Malfunction | CAN Signals not reflected
1407 DEV 05/06/2025 |  | KPIT_TC_DRT_IDS_009,KPIT_TC_DRT_IDS_019 |  |  | 2025-05-06 | Fail | Test_Env_Issue | External Hardware Setup Malfunction | CAN Signals not reflected

## Sheet1
Jira ID | Test Script ID | Bench Number | Test Pack Name | Date | Result | Failure Category | Failure Sub Category | Root Cause Details | Fixation Performed | Issue fixed ? | Additional Information | Transition
DRT-4614 | KPIT_TC_FNC_FM_0638_0001 | Bench06_30AA(R)_DEV | B06_16_30AA_R_KY_AMFM | 27 May 2025 (1407 REL) | Fail | KITE Issue | Image Comparison | Image Comparison failed with 79% | NA
DRT-4614 | KPIT_TC_FNC_FM_0638_0001 | Bench06_30AA(R)_DEV | B06_16_30AA_R_KY_AMFM | 29 May 2025 (1408 DEV) | Pass
DRT-4614 | KPIT_TC_FNC_FM_0638_0001 | Bench06_30AA(R)_DEV | B06_16_30AA_R_KY_AMFM | 4 June 2025 (1408 DEV) | Pass
DRT-4614 | KPIT_TC_FNC_FM_0638_0001 | Bench06_30AA(R)_DEV | B06_16_30AA_R_KY_AMFM | 5 June 2025 (1409 DEV) | Pass

## Sheet2
Jira ID | Test Script ID | Bench Number | Test Pack Name | Date | Result | Failure Category | Failure Sub Category | Root Cause Details | Fixation Performed | Issue fixed ? | Additional Information | Transition
DRT-4614 | KPIT_TC_FNC_FM_0638_0001 | Bench06_30AA(R)_DEV | B06_16_30AA_R_KY_AMFM | 27 May 2025 (1407 REL) | Fail | KITE Issue | Image Comparison | Image Comparison failed with 79% | NA
DRT-4614 | KPIT_TC_FNC_FM_0638_0001 | Bench06_30AA(R)_DEV | B06_16_30AA_R_KY_AMFM | 29 May 2025 (1408 DEV) | Pass